## Slide 1: Project Communications Management
<number>
Notes: <number>

## Slide 2: Project Communications Management Processes
Communications planning: determining the information and communications needs of the stakeholders
Information distribution: making needed information available to project stakeholders in a timely manner
Performance reporting: collecting and disseminating performance information, including status reports, progress measurement, and forecasting
Managing stakeholders: managing communications to satisfy the needs and expectations of project stakeholders and to resolve issues
<number>

## Slide 3: Figure 10-1: Project Communications Management Summary
<number>

## Slide 4: Communications Planning
Every project should include some type of communications management plan, a document that guides project communications
Creating a stakeholder analysis for project communications also aids in communications planning
<number>

## Slide 5: Communications Management Plan Contents
Stakeholder communications requirements
Information to be communicated, including format, content, and level of detail
The people who will receive the information and who will produce it
Suggested methods or technologies for conveying the information
<number>

## Slide 6: Communications Management Plan Contents (continued)
Frequency of communication
Escalation procedures for resolving issues
Revision procedures for updating the communications management plan
A glossary of common terminology
<number>

## Slide 7: Table 10-1: Sample Stakeholder Analysis for Project Communications
<number>

## Slide 8: Information Distribution
Getting the right information to the right people at the right time and in a useful format is just as important as developing the information in the first place
Important considerations include:
  Using technology to enhance information distribution
  Formal and informal methods for distributing information
<number>

## Slide 9: Distributing Information in an Effective and Timely Manner
Don’t bury crucial information
Don’t be afraid to report bad information
Oral communication via meetings and informal talks helps bring important information—good and bad—out into the open
<number>

## Slide 10: Importance of Face-to-Face Communication
Research says that in a face-to-face interaction:
  58 percent of communication is through body language
  35 percent of communication is through how the words are said
  7 percent of communication is through the content or words that are spoken
Pay attention to more than just the actual words someone is saying
A person’s tone of voice and body language say a lot about how he or she really feels
<number>

## Slide 11: Table 10-2: Media Choice Table
<number>

## Slide 12: Other Communication Considerations
Rarely does the receiver interpret a message exactly as the sender intended
Geographic location and cultural background affect the complexity of project communications
  Different working hours
  Language barriers
  Different cultural norms
<number>

## Slide 13: Determining the Number of Communications Channels
As the number of people involved increases, the complexity of communications increases because there are more communications channels or pathways through which people can communicate
Number of communications channels = n(n-1)
2 where n is the number of people involved
<number>

## Slide 14: Figure 10-2: The Impact of the Number of People on Communications Channels
<number>

## Slide 15: Performance Reporting
Performance reporting keeps stakeholders informed about how resources are being used to achieve project objectives
  Status reports describe where the project stands at a specific point in time
  Progress reports describe what the project team has accomplished during a certain period of time
  Forecasts predict future project status and progress based on past information and trends
<number>

## Slide 16: Managing Stakeholders
Project managers must understand and work with various stakeholders
Need to devise a way to identify and resolve issues
Two important tools include:
  Expectations management matrix
  Issue log
<number>

## Slide 17: Table 10-3: Expectations Management Matrix
<number>

## Slide 18: Table 10-4: Issue Log
<number>

## Slide 19: Suggestions for Improving Project Communications
Manage conflicts effectively
Develop better communication skills
Run effective meetings
Use e-mail and other technologies effectively
Use templates for project communications
<number>

## Slide 20: Conflict Handling Modes
Confrontation: directly face a conflict using a problem-solving approach
Compromise: use a give-and-take approach
Smoothing: de-emphasize areas of difference and emphasize areas of agreement
Forcing: the win-lose approach
Withdrawal: retreat or withdraw from an actual or potential disagreement
<number>

## Slide 21: Conflict Can Be Good
Conflict often produces important results, such as new ideas, better alternatives, and motivation to work harder and more collaboratively
Groupthink: conformance to the values or ethical standards of a group; groupthink can develop if there are no conflicting viewpoints
Research suggests that task-related conflict often improves team performance, but emotional conflict often depresses team performance
<number>

## Slide 22: Developing Better Communication Skills
Companies and formal degree programs for IT professionals often neglect the importance of speaking, writing, and listening skills
As organizations become more global, they realize they must invest in ways to improve communication with people from different countries and cultures
It takes leadership to improve communication
<number>

## Slide 23: Running Effective Meetings
Determine if a meeting can be avoided
Define the purpose and intended outcome of the meeting
Determine who should attend the meeting
Provide an agenda to participants before the meeting
Prepare handouts and visual aids, and make logistical arrangements ahead of time
Run the meeting professionally
Build relationships
<number>

## Slide 24: Using E-Mail, Instant Messaging, and Collaborative Tools Effectively
Make sure that e-mail, instant messaging, or collaborative tools are an appropriate medium for what you want to communicate
Be sure to send information to the right people
Use meaningful subject lines and limit the content of emails to one main subject, and be as clear and concise as possible
Be sure to authorize the right people to share and edit your collaborative documents
<number>

## Slide 25: Using Templates for Project Communications
Many technical people are afraid to ask for help
Providing examples and templates for project communications saves time and money
Organizations can develop their own templates, use some provided by outside organizations, or use samples from textbooks
Recall that research shows that companies that excel in project management make effective use of templates
<number>

## Slide 26: Figure 10-3: Sample Template for a Project Description
<number>

## Slide 27: Table 10-5: Sample Template for a Monthly Progress Report
<number>

## Slide 28: Table 10-6: Final Project Documentation Items
<number>

## Slide 29: Lessons Learned Reports
The project manager and project team members should each prepare a lessons-learned report
  A reflective statement that documents important things an individual learned from working on the project
The project manager often combines information from all of the lessons-learned reports into a project summary report
<number>

## Slide 30: Project Archives
It is also important to organize and prepare project archives
Project archives are a complete set of organized project records that provide an accurate history of the project
These archives can provide valuable information for future projects as well
<number>

## Slide 31: Project Web Sites
Many project teams create a project Web site to store important product documents and other information
Can create the site using various types of software, such as enterprise project management software
<number>

## Slide 32: Figure 10-4: Microsoft Office Enterprise Project Management (EPM) Solution
<number>

## Slide 33: Chapter Summary
The goal of project communications management is to ensure timely and appropriate generation, collection, dissemination, storage, and disposition of project information
Main processes include:
  Communications planning
  Information distribution
  Performance reporting
  Managing stakeholders
<number>